## Slide 1: Water System Improvement Project Project Cost Summary Implementation Schedule

## Slide 2: Project Cost Overview
Element | Bond Vote | Current Estimate | Change1 (Unfavorable)
Construction | $4,298,278 | $4,182,340 | $115,938
Engineering | $1,154,520 | $1,697,397 | ($542,877)
Administrative | $17,746 | $41,823 | ($24,077)
Legal | $17,745 | $41,823 | ($24,078)
Land Acquisition | $33,000 | $13,000 | $20,000
Contingency | $643,488 | $188,394 | $455,094
Total Improvements | $6,164,777 | $6,164,777 | $0
Outer District Assistance | $250,000 | $250,000 | $0
Outer District Legal | $0 | $34,954 | ($34,954)
Total Project | $6,414,777 | $6,449,731 | ($34,954)

## Slide 3
Construction Cost Summary
Element | Bond Vote | Current Estimate | Change (Unfavorable)
Contract 1 – East Side Pipe | $576,825 | $577,069 | ($244)
Contract 2 – Water Meters | $720,438 | $0 | $720,438
Contract 3 – Field St Well | $415,040 | $1,065,838 | ($650,798)
Contract 3A – Pressure Valve | $0 | $94,818 | ($94,818)
Contract 4 – East Side Tank & Pipe | $1,438,388 | $1,270,262 | $168,126
Contract 5A – West Side Distribution | $295,872 | $459,815 | ($163,943)
Contract 5B – Taylor Hill (Bluff St.) | $434,109 | $660,302 | ($226,193)
Contract 6 – Park & Chatterton Park | $322,481 | $0 | $322,481
Contract 7 – Existing Tank Removal | $40,000 | $0 | $40,000
Contract 8 – Surface Water Abandon | $55,125 | $54,236 | $889
Total Estimated Construction Cost | $4,298,278 | $4,182,340 | $115,938

## Slide 4: Engineering Cost Summary
4: Town
$790,084
$769,537
Element | Bond Vote | Current Estimate | Change (Unfavorable)
Step I – Preliminary | $218,189 | $219,089 | ($900)
Step II – Final Design | $427,865 | $640,495 | ($212,630)
Step III – Construction Services | $508,466 | $825,813 | ($317,347)
Hydraulic Analysis | $0 | $12,000 | ($12,000)
Total Estimated Engineering Cost | $1,154,520 | $1,697,397 | ($542,877)

## Slide 5: Implementation Schedule
Element | Date
Contract 1 – East Side Pipe | Completed
Contract 2 – Water Meters | Deleted
Contract 3 – Field St Well | Completed
Contract 3A – Pressure Valve | Completed
Contract 4 – East Side Tank & Distribution | Completed
Contract 5A – West Side Distribution | Completed
Contract 5B – Taylor Hill (Bluff Street) | Completed
Contract 6 – Park & Chatterton Park | Deleted
Contract 7 – Existing Tank Removal | Deleted
Contract 8a – Surface Water Discontinuance | December 14, 2014
Contract 8B – Filter Plant Abandonment | December 2018
Hydraulic Analysis | September 2017
Substandard Hydrants | December 2018
Other Improvements - Basis of Design | September 2017